## Summary
Testing | Hours Estimated | Actual Hours (you need to track them) | Tools | Team Member
Functional Testing | 15
Regression Testing | 10 |  | selenium
Performance Testing | 5 |  | visual studio performance profiler, chrome inspection, node. Js framewrok, mysql,and jmeter (optional)
Data preparation | 10 | 5 | pre condition: requirement understanding | Jacquilne
Bug verification | 5 | 5 |  | Yasmin and Neha
Test case writing | 5 to 10 | 5 |  | Lakshay and Neha
Test case review with Dev | 5 to 10 | 5 |  | Whole Team
Other
Training from DEV | 5 | 4
Preparing this plan | 4 | 5
Dev estimation | 10 | 10
Sum before Risk | 64
Risk (10%) | 6.4
Total hours | 70.4

## Requirements
Requirement ID | Title | Hours testing | Type | Actual hours
1 | User can able to add customers | 10 | HW
2 | User can view customers | 5 | SW
3 | Users can search the details | 20 | SW
Total Functional |  | 35

## Testers
.8 percent for testing
Work hours
Tester1 | Neha Ladani – 8708680 | 5
Tester2 | Yasmin Bitar – 8687239 | 5
Test Lead | Lakshay Arora- 8680952 | 10

## Environment
Environment | Operating System | Browser | Task | Team Member
AWS server | Windows 10 | Chrome | For deployment and manual tests | Jacquilene
Local Machine | Windows 10 | Chrome | Automation testing | Neha, Lakshay

## Risk
Risks |  | Level of dammage | Action Plan
Risk1 | Requirements change often | High | We will be following agile methodologies
Risk2 | Late program delivery so short testing | Medium | Focus on more Unit testing and ensure all the test case should pass
Risk3 | Management time between other activities | High | By assigning priorities to task

## Testing Strategy
Testing Types | Expected Hour | Actual Hour
Functional (Blackbox)
Performance
Regression
Automation Testing | 3 | 5

## Dev
Dev Estimation | Expected | Actual
Add Customer | 1 | 1
View Customer | 2 | 1
Search Customer | 1 | 1
Website language framework | 2 | 1
Database creation | 3 | 2
Creating test environment | 1 | 1
| 10 | 7

## Automation Testing
Team Members | Tests | Time estimated | Actual Time | Challenges
Neha Ladani | Setup the environment in local | 0.5 | 0.5 | Doing automation testing for the first time
Lakshay Arora | Test Add Sell data | 0.5 | 1 | Doing automation testing for the first time
| Test View Data | 0.5 | 1
| Test Search functionality | 0.5 | 0.5
| Test Email Format | 0.5 | 1
| Test Year format | 0.5 | 1
|  | 3 | 5
Lakshay
Neha