## Summary
Testing | Hours Estimated | Actual Hours (you need to track them) | Tools | Team Member
Functional Testing | 2
Regression Testing | 2 |  | selenium
Performance Testing |  |  | visual studio performance profiler, chrome inspection, node. Js framewrok, mysql,and jmeter (optional)
Data preparation | 4 | 3 | pre condition: requirement understanding | Jacquilne
Bug verification | 2 | 3 |  | Yasmin and Neha
Test case writing | 3 | 3 |  | Lakshay and Neha
Test case review with Dev | 1 | 3 |  | Whole Team
Other |  | 3
Training from DEV | 1 | 3
Preparing this plan | 2 | 3
Dev estimation | 10 | 3
Sum before Risk | 27
Risk (10%) | 2.7
Total hours | 29.7 | 24

## Requirements
Requirement ID | Title | Hours testing | Type | Actual hours
1 | User can add a new car | 0.25 | SW | 0.5
2 | User can able to view Car details after clicking on link button | 0.25 | SW | 0.5
3 | New cars should appear in the list of view section | 0.25 | SW | 0.5
4 | Mozilla Firefox for automation | 0.25 | SW | 0.5
5 | Customer can search the car if the car exist in view section | 0.25 | SW | 0.5
6 |  | 1.25 |  | 2.5
Total Functional

## Testers
.8 percent for testing
Work hours
Tester1 | Neha Ladani – 8708680 | 3
Tester2 | Yasmin Bitar – 8687239 | 3
Test Lead | Lakshay Arora- 8680952 | 6

## Environment
Environment | Operating System | Browser | Task | Team Member
AWS server | Windows 10 | Mozilla firefox | For all the types of testing(mannual, automation etc.) | Jacquilene
Local Machine | Windows 10 | Mozilla firefox | Automation testing, Development | Neha, Lakshay, Jacquilene

## Risk
Risks |  | Level of dammage | Action Plan
Risk1 | Requirements change often | High | We will be following agile methodologies
Risk2 | Late program delivery so short testing | Medium | Focus on more Unit testing and ensure all the test case should pass
Risk3 | Management time between other activities | High | By assigning priorities to task
Risk4 | Whole team got stuck because test server admin was at different time zone | Critical | More planning was required
Risk5 | Lack of technical knowledge while doing testing | Medium | Did some testing

## Testing Strategy
Testing Types | Expected Hour | Actual Hour
Functional (Blackbox) | 2 | 1
Performance
Regression | 2 | 1
Automation Testing | 4 | 2

## Dev
Dev Estimation | Expected | Actual
Add Car | 1 | 1
View Car | 2 | 1
Search Car | 1 | 1
Website language framework | 2 | 1
Database creation | 3 | 2
Creating test environment | 1 | 1
| 10 | 7

## Automation Testing
Team Members | Tests | Time estimated | Actual Time | Challenges
Neha Ladani | Setup the environment in local | 0.5 | 0.5 | Doing automation testing for the first time
Lakshay Arora | Test Add Sell data | 0.5 | 1 | Doing automation testing for the first time
| Test View Data | 0.5 | 1
| Test Search functionality | 0.5 | 0.5
| Test Email Format | 0.5 | 1
| Test Year format | 0.5 | 1
|  | 3 | 5
Lakshay
Neha